## baselineReqs
Baseline Requirements
notes:
Deployed | Full stack web app runs at provided URL. Updates at each sprint.
GitHub | There is evidence that the team regularl updated progress throughout each sprint.
User Stories | Stories are written in proper format. There is evidence that the team regularly updated progress throughout each sprint.
User API/ Configurable User Authentication/ Sign-up & Login | User can successfully register and login afterwards.
Testing (Unit and or Documented Functional Tests) | Evidence in code and client documentation of tests for all core functionality.
Data Retrieval - Database | Relevant data is properly displayed and appropriate functionality is available (tags, links, filtering).
Responsive | Supports variable screen size.
UX/ UI | User friendly, color schemes.
Client Document | Transfer ownership of application with supporting documentation.
Client Interface | Client can easily update content on web app.
Add 3 APIs | Utilize 3 Web APIs to enhance functionality. Ex: payment processing, scheduling, mapping, social media

## release
| Deliverable |  | start | end | weeksRemaining | daysRemaining
Sprint1 |  |  | 2020-02-17 | 2020-03-10 | 2 | 5
Requirements Gathering
User Story Creation, sizing, and assignments
User interactin design/ wireframing and feedback
Technology stack design
Technology stack setup
Basic functionality
Sprint2 |  |  | 2020-03-16 | 2020-03-31 | 5 | 5
UI and Backend
-most functionality complete
-testing
Initial documentation
UX testing
Final UI look-and-feel design
Sprint3 |  |  | 2020-04-06 | 2020-04-21 | 8 | 5
Bug fixes
Final/ new features
Final documentation
Final "branding" - logo, look-and-feel
Formulas:
weeksRemaining = QUOTIENT(([end] - TODAY()),7)
daysRemaining = MOD(([end] - TODAY()),7)

## sprint2
s