## careerFindStoryMap
| Epic: Content Management | Epic: Primary View | Epic: Multi-User Accounts |  | Epic: Chat Career Counselor | Epic: Point-Based Progress Tracker
| Theme: Manage content. | Theme: View content. | Theme: User Management | Theme: User Login Page | Theme: Career Recommendations | Theme: Progress Tracker
Base System | As a Counselor I want to manage (CRUD) the carrer clusters ( name, icon, keyword associations) displayed on the site. | As a User I want to see a list of career clusters (name, icon) after logging into the site so that I can drill down into associated careers for each cluster.
| As a Counselor I want to manage (CRUD) the keywords (name, type: subject, interest) used to associate career clusters, careers, and celebrities. | As a User after clicking on a career name I want to see base career data (name, salary, key subjects, description) and keyword-associated content links presneted on a page.
| As a Counselor I want to manage (CRUD) careeers (name, salary, description, keyword associations) displayed on the site. | As a User after clicking on a DITL link from an associated career page I would like to see that career's DITL article presented on a page.
| As a Counselor I want to manage (CRUD) Day-In-the-Life articles that are associated with careers. | As a User after clicking on a celebrity link from an associated career page I would like to see that career's celebrity profile (name, photo, article) presented on a page.
As a Counselor I want to manage (CRUD) the celebrity profiles (name, photo, article, keyword associations) displayed on the site.
Minimum Viable Product |  |  | As an Admin I would like to manage (CRUD) all user types (student, teacher, counselor, admin) from a listing of all users in the system. | As a User I should be able to access the site with valid credentials (username/ password or e-mail/ password) from a login page.
As an Admin I should be able to reset the password of any listed user in the system.
As an Admin I want to manage (CRUD) groups (name, associated users) in the system.
As a Teacher I want to manage (CRUD) students in my associated group (class).
As a Teacher I want to (CRUD) sub-groups (name, associated users) within my group (class).
As a Teacher I should be able to reset the password of students within my group (class).
Base Chat Counselor | As a Counselor I want to manage (CRUD) prompts that will be presented to students when they log into the site. |  |  |  | As a Student I want to answer a chat prompt after logging into the site and receive a career cluster recommendation based on parsed keywords in my response.
| As a Counselor I want to manage (CRUD) an icon/ profile picture that will be used by the site's chat counselor. |  |  |  | As a Student I want to my response to be logged if it does not contain any known keywords so that my Counselor can improve the system.
As a Counselor I want to be able to view and delete (RD) anonymized student response logs that did not contain any keywords present in the system.
Enhanced Recommendations |  |  |  |  | As a Student I want recommended career clusters to be placed in a queue so that I can remember to visit them.
As a Student I want keywords parsed from my responses to be stored so that future recommendations take them into account.
As a Student I should be able to bookmark careers I am interested in.
Reward System |  |  | As a Teacher I can view point totals of students and student groups within my class. |  |  | As a Student I earn 1 point each time I visit a new career and all associated content.
|  |  | As a Teacher I can reset point totals of students and groups within my class. |  |  | As a Student my viewed content should be tracked in my account.
As a Student I should be able to view my current point total.
As a Student I can view the point total of any groups I belong to.

## backlog
ID | Grouping | User Story | Estimate | Sprint1 | Sprint2 | Sprint3 | US/TC | Front-End | Back-End | Testing | API
CF01 | BASE | As a Counselor I want to manage (CRUD) the carrer clusters ( name, icon, keyword associations) displayed on the site. | 0
CF02 | BASE | As a Counselor I want to manage (CRUD) the keywords (name, type: subject, interest) used to associate career clusters, careers, and celebrities. | 0
CF03 | BASE | As a Counselor I want to manage (CRUD) careeers (name, salary, description, keyword associations) displayed on the site. | 0
CF04 | BASE | As a Counselor I want to manage (CRUD) Day-In-the-Life articles that are associated with careers. | 0
CF05 | BASE | As a Counselor I want to manage (CRUD) the celebrity profiles (name, photo, article, keyword associations) displayed on the site. | 0
CF06 | BASE | As a User I want to see a list of career clusters (name, icon) after logging into the site so that I can drill down into associated careers for each cluster. | 0
CF07 | BASE | As a User after clicking on a career name I want to see base career data (name, salary, key subjects, description) and keyword-associated content links presneted on a page. | 0
CF08 | BASE | As a User after clicking on a DITL link from an associated career page I would like to see that career's DITL article presented on a page. | 0
CF09 | BASE | As a User after clicking on a celebrity link from an associated career page I would like to see that career's celebrity profile (name, photo, article) presented on a page. | 6 | 6 |  |  | 1 | 2 |  | 1 | 2
CF10 | MVP | As an Admin I would like to manage (CRUD) all user types (student, teacher, counselor, admin) from a listing of all users in the system. | 0
CF11 | MVP | As an Admin I should be able to reset the password of any listed user in the system. | 0
CF12 | MVP | As an Admin I want to manage (CRUD) groups (name, associated users) in the system. | 0
CF13 | MVP | As a Teacher I want to manage (CRUD) students in my associated group (class). | 0
CF14 | MVP | As a Teacher I want to (CRUD) sub-groups (name, associated users) within my group (class). | 0
CF15 | MVP | As a Teacher I should be able to reset the password of students within my group (class). | 0
CF16 | MVP | As a User I should be able to access the site with valid credentials (username/ password or e-mail/ password) from a login page. | 0
CF17 | baseChat | As a Counselor I want to manage (CRUD) prompts that will be presented to students when they log into the site. | 0
CF18 | baseChat | As a Counselor I want to manage (CRUD) an icon/ profile picture that will be used by the site's chat counselor. | 0
CF19 | baseChat | As a Counselor I want to be able to view and delete (RD) anonymized student response logs that did not contain any keywords present in the system. | 0
CF20 | baseChat | As a Student I want to answer a chat prompt after logging into the site and receive a career cluster recommendation based on parsed keywords in my response. | 0
CF21 | baseChat | As a Student I want to my response to be logged if it does not contain any known keywords so that my Counselor can improve the system. | 0
CF22 | enhChat | As a Student I want recommended career clusters to be placed in a queue so that I can remember to visit them. | 0
CF23 | enhChat | As a Student I want keywords parsed from my responses to be stored so that future recommendations take them into account. | 0
CF24 | enhChat | As a Student I should be able to bookmark careers I am interested in. | 0
CF25 | rewardSys | As a Teacher I can view point totals of students and student groups within my class. | 0
CF26 | rewardSys | As a Teacher I can reset point totals of students and groups within my class. | 0
CF27 | rewardSys | As a Student I earn 1 point each time I visit a new career and all associated content. | 0
CF28 | rewardSys | As a Student my viewed content should be tracked in my account. | 0
CF29 | rewardSys | As a Student I should be able to view my current point total. | 0
CF30 | rewardSys | As a Student I can view the point total of any groups I belong to. | 0
|  | Total/ Loading: | 6 | 6 | 0 | 0