## baselineReqs
Baseline Requirements
Have we planned to meet these requirements?
Deployed | Full stack web app runs at provided URL. Updates at each sprint. | yes
GitHub | There is evidence that the team regularl updated progress throughout each sprint. | yes
User Stories | Stories are written in proper format. There is evidence that the team regularly updated progress throughout each sprint. | yes
User API/ Configurable User Authentication/ Sign-up & Login | User can successfully register and login afterwards. | yes - Multi-user System - Login Screen Item
Testing (Unit and or Documented Functional Tests) | Evidence in code and client documentation of tests for all core functionality. | yes - I am suggesting documented functional tests (use cases with trimmings)
Data Retrieval - Database | Relevant data is properly displayed and appropriate functionality is available (tags, links, filtering). | yes - mentioned in user requirements
Responsive | Supports variable screen size. | yes - no associated items though, maybe add to UR?
UX/ UI | User friendly, color schemes. | yes
Client Document | Transfer ownership of application with supporting documentation. | yes… docs in rep
Client Interface | Client can easily update content on web app. | yes - content management item in base system
Add 2 APIs | Utilize 2 Web APIs to enhance functionality. Ex: payment processing, scheduling, mapping, social media | ? Does mongoDB count as an API ? Can we use an API for the chatbot somehow… preferably for a simplified implementation?

## release
| Deliverable |  | start | end | weeksRemaining | daysRemaining
Sprint1 |  |  | 2020-02-24 | 2020-03-10 | 2 | 1
Requirements Gathering
User Story Creation, sizing, and assignments
User interactin design/ wireframing and feedback
Technology stack design
Technology stack setup
Basic functionality
Sprint2 |  |  | 2020-03-16 | 2020-03-31 | 5 | 1
UI and Backend
-most functionality complete
-testing
Initial documentation
UX testing
Final UI look-and-feel design
Sprint3 |  |  | 2020-04-06 | 2020-04-21 | 8 | 1
Bug fixes
Final/ new features
Final documentation
Final "branding" - logo, look-and-feel
Formulas:
weeksRemaining = QUOTIENT(([end] - TODAY()),7)
daysRemaining = MOD(([end] - TODAY()),7)

## sprint2
s